## Sheet1
Task name | 担当 | [27 empty] | April | [28 empty] | Additional information
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
|  | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun.
Stage 3
ETMY tuning | Miyamoto | bar: 19 Mon. to 23 Fri.; 26 Mon. to 30 Fri.
TMS alignment at ETMY | Akutsu | bar: 19 Mon. to 23 Fri.; 27 Tue. to 30 Fri.
Installation of ETMX | Tomaru | bar: 19 Mon. to 20 Tue.
Connection payload and Type-A tower | Tomaru, Takahashi | bar: 21 Wed.
Cabling | Tomaru | bar: 20 Tue. to 23 Fri.; 26 Mon.
Setting oplevs | Akutsu | bar: 22 Thur. to 23 Fri.; 26 Mon. to 27 Tue.
ETMX control test | bar: 26 Mon. to 30 Fri.; April 2 Mon. to April 6 Fri.
IFO control | Enomoto | bar: 27 Tue. to 30 Fri.; April 2 Mon. to April 6 Fri.
Removal of assembly setup | Tomaru | bar: April 9 Mon. to April 12 Thur.
Closing EXC | Kimura | bar: April 9 Mon. to April 12 Thur.
Beam alingment | Izumi | bar: April 16 Mon. to April 20 Fri.
ETMX pump down | Kimura | bar: April 12 Thur. to April 17 Tue.
ETMX leak check | Kimura | bar: April 18 Wed. to April 20 Fri.
IFO control | Izumi | bar: April 16 Mon. to April 20 Fri.
Operation | All | [56 empty] | 4/23-5/1 | bar: April 23 Mon. to April 29 Sun.
Remove EXA PD | Yokozawa | bar: 27 Tue. to 28 Wed.
Pcal alignment | Inoue | bar: 26 Mon. to 30 Fri.; April 2 Mon. to April 6 Fri.
Pcal window replacement | Yokozawa | bar: April 5 Thur. to April 6 Fri.
Pcal periscope reharsal | Inoue | bar: April 5 Thur.
Wab cooling | Akutsu | bar: 22 Thur. to 27 Tue.
ISS or others | Sakamoto | bar: 23 Fri.; 26 Mon. to 27 Tue.