## Sheet1
Task name | 担当 | [14 empty] | Jan. | [30 empty] | Feb. | [10 empty] | Additional information
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
|  | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun.
Stage 2
アラインメント再確認 | 和泉 | bar: Jan. 11 to Jan. 12
ETMY PD付きバッフル | 牛場、都丸 | bar: Jan. 5; Jan. 9 to Jan. 12; Jan. 15 to Jan. 17
ETMY hierarchical damping | 牛場
ETMY真空チェック、冷却開始打ち合わせ | 宮川 | [56 empty] | 12時30分ファン小屋 | bar: Jan. 10
EYAカメラ高速化 | 井上 | bar: Jan. 15 to Jan. 16
EYA振動試験 | bar: Jan. 9 to Jan. 10; Jan. 24 to Jan. 25
EYA機器制御配線 | 麻生、都丸 | bar: Jan. 12
EYC真空排気 | 木村 | bar: Jan. 18 to Jan. 22
EYCターボポンプ始動 | 木村 | bar: Jan. 19 to Jan. 23
EYCリークテスト | 木村 | bar: Jan. 24 to Jan. 25
EYC冷却 | 木村 | bar: Jan. 25 to Jan. 29
Beam alignment to REFL | 和泉 | bar: Jan. 29 to Feb. 2; Feb. 5 to Feb. 9
IYC大気開放 | 木村 | bar: Jan. 15 to Jan. 19
IYA 床面養生、COACH鏡板開放 | 木村 | bar: Jan. 15 to Jan. 17
IYA架台組み込み | 木村 | [56 empty] | 機材通過不可、人は通行可能 | bar: Jan. 18 to Jan. 19
ITMカメラセット | 井上 | bar: Jan. 16 to Jan. 18
IXCアンカー打設 | 木村 | bar: Jan. 15 to Jan. 19
IXC清掃 | 木村 | bar: Jan. 23 to Jan. 25
WAB準備 | 阿久津 | bar: Jan. 15 to Jan. 19
WAB試験 | 阿久津 | [56 empty] | 2月までに配線、蓋閉じ。 | bar: Jan. 22 to Jan. 26
ISS, IMC ASC | 苔山 | bar: Jan. 15 to Jan. 19
PMC installation, tilt sensor | 苔山 | bar: Jan. 22 to Jan. 26
Stage 3
ETMX到着 | [57 empty] | 2月5日前後 | bar: Feb. 5 to Feb. 9
ETMX installation | [57 empty] | 3月下旬
ETMX damping | [57 empty] | 4月初め
ETMX alignment | [57 empty] | 4月初め
IFO lock | [57 empty] | 4月上旬
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
|  | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun.
Laser Hazard | bar: 1 to 4
Behind IFI line
Behind IMM line | bar: 1 to 11
Behind SR2-SR3 line | bar: 1 to 4; 11 to 11
Xend 1F | bar: 1 to 4; 6 to 7
Xend 2F | bar: 1 to 4; 6 to 7
Yend 1F | bar: 1 to 4; 6 to 7
Yend 2F | bar: 1 to 4; 6 to 7