## Sheet1
Task name | 担当 | [17 empty] | February | [29 empty] | March | [8 empty] | Additional information
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
|  | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun.
Stage 2
Leak check | Kimura | [56 empty] | リーク箇所が見つかった | bar: 29 to 30
EYV支持構造リリース | Kimura | bar: 31
Yend gate valve open | Kimura | bar: 31
Rechecking beam alignment | Izumi | bar: 31 to February 1
Check ETMY | Izumi | bar: February 1 to February 6
ETMY ventig | Kimura | [56 empty] | depends on EMY | bar: February 7 to February 8
Leak check | bar: February 14 to February 15
ETMY pumpdown | Kimura | [56 empty] | depends on EMY | bar: February 19 to February 23
EYC冷却 | Kimura | [56 empty] | possibly delayed | bar: February 26 to February 2
Beam alignment to REFL | Izumi | [56 empty] | possibly delayed | bar: March 5 to March 9
WAB test | Akutsu | [56 empty] | 3月くらいまで。 | bar: 29 to February 2
PMC installation | Kokeyama | bar: 30 to 31
Stage 3
Arrival of ETMX at Kamioka | bar: March 9
Installation of ETMX | [57 empty] | 3/12-16
Connection payload and Type-A tower | [57 empty] | 3/19-23
Cabling | [57 empty] | 3/19-23
Removal of assembly setup | [57 empty] | 3/26-30
Closing EXC | [57 empty] | 3/26-30
Oplev anchor | [57 empty] | 4/2-6
Cleaning | [57 empty] | 4/2-6
Setting oplevs | [57 empty] | 4/2-6
ETMX control test | [57 empty] | 4/9-13
Beam alingment | [57 empty] | 4/16-20
IFO control | [57 empty] | 4/16-20
Pump down | [57 empty] | 4/23-27
Leak check | [57 empty] | 4/23-27
Operation | [57 empty] | 4/30-5/7
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
|  | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun.
Laser Hazard
PSL
Behind IMM line | bar: 31 to 1; 6 to 11
Behind SR2-SR3 line | bar: 1 to 14; 31 to 1; 19 to 11
Yend 1F | bar: 31 to 1; 19 to 11