## Sheet1
Task name | 担当 | [40 empty] | March | [15 empty] | Additional information
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun.
Stage 2
Rechecking beam alignment | Izumi
Check ETMY | Izumi | bar: 5 to 6
EYC冷却 | Kimura | [56 empty] | Takes 3weeks. | bar: 7 to 11
Beam alignment to REFL | Izumi | bar: 19 to 23; 26 to 2
WAB test | Akutsu | [56 empty] | Until March | bar: 5 to 9
WAB closing | Akutsu | bar: March 12 to March 16
WAB cooling | Akutsu | [56 empty] | April?
Stage 3
Arrival of ETMX at Kamioka | bar: March 9
Installation of ETMX | [57 empty] | 3/12-16 | bar: March 12 to March 16
Connection payload and Type-A tower | [57 empty] | 3/19-23
Cabling | [57 empty] | 3/19-23
Removal of assembly setup | [57 empty] | 3/26-30
Closing EXC | [57 empty] | 3/26-30
Oplev anchor | [57 empty] | 4/2-6
Cleaning | [57 empty] | 4/2-6
Setting oplevs | [57 empty] | 4/2-6
ETMX control test | [57 empty] | 4/9-13
Beam alingment | [57 empty] | 4/16-20
IFO control | [57 empty] | 4/16-20
Pump down | [57 empty] | 4/23-27
Leak check | [57 empty] | 4/23-27
Operation | [57 empty] | 4/30-5/7
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun.
Laser Hazard
PSL
Behind IMM line
Behind SR2-SR3 line
Yend 1F