## Sheet1
Task name | 担当 | [23 empty] | February | March | [31 empty] | Additional information
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1
|  | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun.
Stage 3
Power outage at surface building
ETMY tuning | Enomoto | bar: 19 to 23
Beam alignment to REFL | Izumi | bar: 26 to March 2
Height adjustment for PR suspensions | Aso | bar: February 28
IFO realignment | Izumi | bar: March 1 to March 2
Changing green items in PR2 | Akutsu | bar: March 5 to March 9
TMS installation at ETMY | Akutsu | bar: March 12 to March 16
TMS alignment at ETMY | Akutsu | bar: March 19 to March 23
Duct connections at the corner area | Uchiyama | [56 empty] | No beam | bar: March 12 to March 16
Coner area vacuum test | Uchiyama | bar: March 19 to March 23
ETMX measurement done | Okutomi | bar: 26 to March 2
Preparation for ETMX installtion | bar: March 5 to March 9
Arrival of ETMX at Kamioka | bar: March 9
Installation of ETMX | bar: March 12 to March 16
Connection payload and Type-A tower | bar: March 19 to March 23
Cabling | bar: March 19 to March 23
Setting table for ETMX oplevs | bar: 26 to 27
Setting oplevs | [57 empty] | 3/19-4/6 | bar: March 19 to March 23; March 26 to March 30
ETMX control test | [57 empty] | 3/26-4/6 | bar: March 26 to March 30
IFO control | [57 empty] | 3/26-4/6 | bar: March 26 to March 30
Removal of assembly setup | [57 empty] | 4/9-13
Closing EXC | [57 empty] | 4/9-13
Beam alingment | [57 empty] | 4/16-20
ETMX pump down | [57 empty] | 4/12-13
ETMX leak check | [57 empty] | 4/18-20
IFO control | [57 empty] | 4/16-20
Operation | [57 empty] | 4/23-5/1
WAB test | Akutsu | [56 empty] | Until March
WAB closing | Akutsu | [56 empty] | No beam | bar: March 8 to March 9
Wab cooling | Akutsu | [56 empty] | April?
ISS or others | Kokeyama | bar: 19 to 23
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
|  | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun.
Laser Hazard
PSL
Behind IMM line | bar: 13 to 32
Behind SR2-SR3 line | bar: 1 to 14; 22 to 27; 1 to 4; 19 to 32
Yend 1F