## Sheet1
Task name | 担当 | [41 empty] | April | [14 empty] | Additional information
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun.
Stage 3
ETMY tuning | Miyamoto | bar: 5 to 9; 12 to 16
Beam alignment to REFL | Enomoto | bar: 6
IFO realignment | Enomoto | bar: 5; 16; 19
Changing green items in PR2 | Akutsu | bar: 5 to 6
Green alignment to ETMY | Akutsu | bar: 6 to 7
TMS installation at ETMY | Akutsu | bar: 12 to 16
TMS alignment at ETMY | Akutsu | bar: 19 to 23
Duct connections at the corner area | Uchiyama | bar: 12 to 16
Coner area vacuum test | Uchiyama | bar: 19 to 23
Preparation for ETMX installtion | Tomaru | bar: 5 to 9
Arrival of ETMX at Kamioka | Ushiba | bar: 9
Installation of ETMX | Tomaru | bar: 12 to 16
Connection payload and Type-A tower | Tomaru, Takahashi | bar: 19 to 23
Cabling | Tomaru | bar: 19 to 23
Setting oplevs | bar: 22 to 23
ETMX control test | bar: 26 to 30; April 2 to April 6
IFO control | bar: 26 to 30; April 2 to April 6
Removal of assembly setup | [57 empty] | 4/9-13 | bar: April 9 to April 13
Closing EXC | [57 empty] | 4/9-13 | bar: April 9 to April 13
Beam alingment | [57 empty] | 4/16-20
ETMX pump down | [57 empty] | 4/12-13
ETMX leak check | [57 empty] | 4/18-20
IFO control | [57 empty] | 4/16-20
Operation | [57 empty] | 4/23-5/1
WAB closing | Akutsu | bar: 8
Wab cooling | Akutsu | bar: 22 to 26
ISS or others | Kokeyama
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun.
Laser Hazard
PSL
Behind IMM line | bar: 13 to 15
Behind SR2-SR3 line | bar: 1 to 5; 19 to 15
Yend 1F