## Sheet1
Task name | 担当 | [14 empty] | May/June | [34 empty] | Additional information
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1
|  | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun.
Phase 2 Stage 1
iMC repare | bar: May/June 28 to May/June 1
iMC alignment with high power | [50 empty] | Needs high power upto IMMT | bar: May/June 6
IMMT repare | bar: May/June 5 to May/June 8; May/June 11 to May/June 15; May/June 18 to May/June 22
PMC installtion | bar: May/June 6 to May/June 8; May/June 11 to May/June 15
High power laser installtion | bar: May/June 11 to May/June 15; May/June 18 to May/June 22
ITMX rack cable connection | bar: May/June 11 to May/June 15
NAB installtion | bar: May/June 6 to May/June 8; May/June 11 to May/June 15
Setting heat link at ETMX | bar: May/June 5 to May/June 6
Center vacuum
ETMX vacuum | bar: May/June 28 to May/June 30; May/June 7 to May/June 1
ETMX cooling | bar: May/June 18 to May/June 1
ETMY vacuum | bar: May/June 13 to May/June 1
ETMY cooling
ITMX vacuum
ITMX cooling
ITMY vacuum
ITMY cooling