## Sheet1
Task name | 担当 | [14 empty] | June | [19 empty] | July | [14 empty] | Additional information
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun.
Phase 2, HPL stage
iMC alignment with high power | [50 empty] | Needs high power upto IMMT | bar: June 12
iMC re-lock | bar: June 21 to June 22; June 27
IMMT1 repare | bar: June 11 to June 15; June 18 to June 22
IMMT2 repare | [50 empty] | for 2weeks | bar: July 9 to July 13
PMC installtion | bar: June 11 to June 15
High power laser installtion | [50 empty] | delayed, after end of July | bar: June 12 to June 15
ITMX rack cable connection | bar: June 11 to June 13
NAB installtion | [50 empty] | at X front | bar: June 11 to June 15; June 18 to June 22; June 25 to June 29
ITMX arrival at Kamioka | bar: June 16
Setting heat link at ETMX
Center vacuum | bar: June 13 to July 15
ETMX vacuum | bar: June 11 to July 15
ETMX cooling | bar: June 27 to July 15
ETMY vacuum | bar: June 15 to July 15
ETMY cooling
ITMX vacuum
ITMX cooling
ITMY vacuum
ITMY cooling
requires lazer | bar: July 8; July 15