## Sheet1
Task name | 担当 | [14 empty] | June | [5 empty] | July | [28 empty] | Additional information
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
|  | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun.
Phase 2, HPL stage
iMC re-lock | bar: June 25 Mon. to June 27 Wed.
IMMT2 repare | [50 empty] | for 2weeks | bar: July 9 Mon. to July 13 Fri.; July 16 Mon. to July 20 Fri.
High power laser installtion | [50 empty] | delayed, after end of July
NAB installtion | [50 empty] | at X front | bar: June 25 Mon. to June 29 Fri.
ETMY arrival at Kamioka | bar: July 27 Fri.
Center vacuum | bar: June 25 Mon. to July 29 Sun.
ETMX vacuum | bar: June 25 Mon. to July 29 Sun.
ETMX cooling | bar: June 29 Fri. to July 29 Sun.
ETMY vacuum | bar: June 25 Mon. to July 29 Sun.
ETMY cooling
ITMX vacuum | [50 empty] | 8/27 door closing and start pumpdown
ITMX cooling
ITMY vacuum | [50 empty] | 8/27 door closing
ITMY cooling
PAB | bar: July 25 Wed. to July 27 Fri.
requires lazer | bar: July 29 Sun.