## Slide 1: Commissioning plan for Phase 1 (Preliminary draft)
Seiji Kawamura and Osamu Miyakawa
with the inputs from Uchiyama, Michimura, and others
JGW-G1707090-v1

## Slide 2: Objectives and scope of commissioning
According to the roadmap established by SEO, the commissioning team should execute the commissioning activities.
The commissioning activities are to coordinate the various tasks of each subsystem whenever necessary to accomplish the successful operation of the fully-equipped detector with the target sensitivity and duty factor.
Independent installation/integration activities of each subsystem are not included in the scope of commissioning.

## Slide 3: Goal for phase 1
Strict requirement: operation of the cryogenic 3km Michelson interferometer by Mar. 30, 2018
  Mar. 31 reserved for a test run
However, we should complete the phase 1 operation as soon as possible.

## Slide 4: Stages in Phase 1
There are four stages in Phase 1:
Stage 1 (Oct. 2 - End of Oct.)
  Alignment up to BS (inclusive)
Stage 2 (Dec.)
  Alignment of ETMy
Stage 3 (Feb.)
  Locking of MI with Cryogenic ETMy with Calibrated sensitivity curve
Stage 4 (Mar.)
  Locking of MI in vacuum with cryogenic ETMx/y with data stored
Test run (One day before cooling Xend; Mar. 31 – April-GW)
  Characterization of various systems for Phase 2
(No PRMI operation after test run)

## Slide 5: Stage 1
Initial status
  Beam from IMMT2 roughly aligned to PRM and BS
  PRM, PR2, PR3, and BS installed and integrated

## Slide 6: Rough Schedule
 | 9/25-9/29 | 10/2-10/6 | 10/10-10/13 | 10/16-10/20 | 10/23-10/27 | 10/30-11/2 | 11/6-11/10
BS integration |  |  |  |  |  |  | 
Preparation of EXA |  |  |  |  |  |  | 
Preparation of EXY |  |  |  |  |  |  | 
Preparation of IXA |  |  |  |  |  |  | 
Preparation of IYA |  |  |  |  |  |  | 
Placement of beam tubes, etc. |  |  |  |  |  |  | 
Alignment of IMMT2, PR2 |  |  |  |  |  |  | 
Alignment of PR3 |  |  |  |  |  |  | 
Alignment of BS |  |  |  |  |  |  | 
Measurement of beam position at IXC, IYC |  |  |  |  |  |  | 
Positioning of IMMT1/2 or PR2/3 |  |  |  |  |  |  | 

## Slide 7: 検討事項１
クリーンブース内の敷物
  齊藤さんの意見：○○Cについては重量物を扱うのでステンレスの方がよいが、○○AについてはGマットでいいんじゃないか
  古田さんの意見：Gマットはクリーンエリアでも使えると思う
  麻生君の意見：実際に表面を触ってチェックしたが問題ないと思う
１０月第一週の真空ダクトの設置等
  齊藤さんが現在調整中（ほぼOK)
通路の撤去
  齊藤さんの意見：エアーを入れるのは大変なので、作業をする前にさっとずらして終わったらすみやかに元に戻した方がいいのでは？

## Slide 8: Preparation (EXA/EYA)
Expose the EYA to air (CRY)
Loosen the bellows and Install the flange behind the EXA/EYA (CRY)
Clean the EXA/EYA area with Korokoro (CAL?)
Place the stainless or white sheet (to be decided soon) on the floor
Preparation of miscellaneous items (MIF via Aso, Sakamoto)
  iKAGRAで使用した機材の確認
    ラップ梱包された状態でクリーンブース外で保管。
    クリーンブースに搬入する前にラップ表面を拭き取り清掃する必要有り。
    クリーンブース内でラップを外して機材表面も簡単な清掃を行うべき。
  必要物品
    消耗品類（ベンコット、アルコール、ウエットティッシュ等）を購入。
    工具（メガネレンチ、トルクレンチ）を調達。
    クリーンウエアに着替える際に必要なハンガー等を調達。

## Slide 9: Preparation (IXA/IYA)
clean the area (CRY)
Expose IXA to air; not necessary to clear IXA (CRY)
Expose IYA and partially clear IYA (CRY)
Place the stainless or white sheet (to be decided soon) on the floor
Preparation of goods (MIF via Aso, Sakamoto）
  消耗品類（ベンコット、アルコール、ウエットティッシュ等）
  工具（メガネレンチ、トルクレンチ）等
  クリーンウエアに着替える際に必要なハンガー等
  バスマット

## Slide 10: Placement of Beam tubes, etc.
Purchase of UHV aluminum foil (Aso)
PR2-PR3 beam tube
  Install PR2-PR3 beam tube with the connection part covered by aluminum foil instead of installing the bellows, Inject dry air into PR2-PR3 beam tube (?)
BS assembly frame
  Remove BS assembly frame
BS-beam tubes
  Install BS beam tube with the connection part covered by aluminum foil instead of installing the bellows, Inject dry air into BS-beam tube (?)
IFI-IMM, IMM-PRM, PRM-PR3
  TBD

## Slide 11: Alignment
Alignment up to virtual positions of ETMx/ETMy
  10/10 – 10/13: Misalign PRM by a known amount (VIS, MIF), Align IMMT2 (IOO) and PR2 (VIS)
  10/16 – 10/20: Align PR3 by monitoring beam in IXA and EXA (MIF, VIS)
  10/23 – 10/27: Align BS by monitoring beam in IYA and EYA (MIF, VIS)

## Slide 12: Measurement of beam position at IXC, IYC
IXC、IYCでのビーム位置の測定
いつ？誰が？精度1mm?

## Slide 13: Positioning of IMMT1/2 or PR2/3
Tune IMMT1/2 or PR2/3 position by monitoring beam profile by PD in EXA/EYA (MIF, VIS, IOO)
可能か？
いつ？誰が？

## Slide 14: 検討事項２
PR、BSのインストール後、PR,BSミラーのタンクとの相対位置をFAROで測定したい；1週間（正田）
真空チェックを11月にやってはどうか？（木村）
  PR3,BS等間の真空ダクトの接続
  PR3,BS等の真空引きとダクト接続部等の真空リーク試験＋真空ポンプの動作確認
  真空引きによるPR3,BS等のアライメント再調整の必要かの確認

## Slide 15: Stage 2
Initial status
  Beam from BS to virtual positions of ETMx/ETMy finely aligned
  ETMy installed and integrated in the air at room temperature

## Slide 16: Activities
Alignment of ETMy
  Align ETMy to IFI (MIF, DGS, VIS, CRY, IOO)
  Lead MI-REFL beam outside the chamber (MIF, IOO)
Installation and alignment of MI-REFL output optics
  Install and align MI-REFL output optics using the beam reflected by ETMy (MIF)
Bellows connection and evacuation of the EYC/EYA (CRY)

## Slide 17: Stage 3
Initial status
  MI aligned except ETMx
  ETMx installed in the air at room temperature
  EYC evacuated

## Slide 18: Activities
RT model for LSC and calibration (DGS, MIF, CAL)
Global control between LSC and VIS models (DGS, MIF, VIS)
Alignment, locking, optimization, characterization of MI
  Align ETMy to IFI (MIF, DGS, VIS, CRY, IOO)
  Make a fine alignment of MI (MIF)
  Lock MI (MIF)
  Optimize and characterize MI (MIF)
Installation and alignment of MI-AS output optics (MIF, VIS)
Cooling-down of ETMy (CRY)
  鏡角度の追跡 シフト？
Calibration (CAL)

## Slide 19: Stage 4
Initial status
  MI locked
  ETMy cooled down

## Slide 20: Activities
Bellows connection and evacuation of the EXC/EXA and cooling-down of ETMx (VAC, CRY)
Bellows connection and evacuation of the whole vacuum system in the center area (VAC)
Re-alignment, re-locking, optimization, characterization of MI (MIF)
Guardian scripts for PSL/IMC/MI (DGS, IOO, MIF)
Data pipe line (DAS)
Physical environment monitors (DetChar)
Selection of monitoring signals (DGS)

## Slide 21: Expected final status
The whole vacuum chamber evacuated
ETMx/ETMy cooled down
MIF re-aligned, locked, optimized
Automatic operation for MI
Detchar system
Various signals integrated into data acquisition system
Various signals monitored at control room

## Slide 22: Laser hazard area
The laser hazard area should be set for the minimum area not to disturb necessary installation/integration work.

## Slide 23: Organization of commissioning team
Organization
  Leader: Kawamura
  Sub-leader: Miyakawa
With the help of
  Scheduler: Uchiyama
  MIF chief: Michimura
  Each subsystem chief/subchief
The commissioning team is a subset of SEO.

## Slide 24: Role of commissioning team
The team establishes the detailed schedule following the overall schedule established by SEO and scheduler.
The team coordinates work of each subsystem to follow the detailed schedule.
At least one of the team members stays at the site everyday during the commissioning period.
When a possible delay of the schedule is anticipated, the team tries to manipulate the order of daily work, etc. to meet the schedule if possible. If not, the team reports to the SEO and asks for the remedy.
The MIF chief helps the team by suggesting the optimized procedure of the commissioning task from the standpoint of the interferometer operation.

## Slide 25: Meeting
The commissioning leader runs a weekly remotely-accessible meeting with the help of sub-leaders inside the “Kotei-kaigi” to discuss activities on the previous week and on the coming weeks.
  The team encourages people off site to attend the weekly meeting remotely to provide their inputs.
The leader runs a daily remotely-accessible meeting inside the “Chorei” to discuss activities on the previous day and on the day .
  The team encourages people off site to attend the daily meeting remotely to provide their inputs.

## Slide 26: Remote operation (under discussion)
In principle the remote operation from anywhere other than Kamioka (KAGRA site and control room) is prohibited.
If absolutely necessary, remote operation is possible under the following conditions:
  The remote operation should be approved by the commissioning team in advance.
  The corresponding researcher should be present at Kamioka.
  The remote operation should be mentioned in the daily meeting in Chorei.
The remote viewing is OK.

## Slide 27: TBD
We will talk with each subsystem group to optimize the detailed schedule.
  When should the GIF data be implemented in the digital system.
  What kind of evaluation and measurement should be done at each stage?
  When should the bellows in the central area be connected. When should the whole vacuum system in the center area be evacuated? Before or after the first half of the test run?
How long should the test run last?