## Slide 1: Commissioning plan for Phase 1 (Preliminary draft)
Seiji Kawamura and Osamu Miyakawa
with the inputs from Uchiyama, Michimura, and others
JGW-G1707090-v?

## Slide 2: Objectives and scope of commissioning
According to the roadmap established by SEO, the commissioning team should execute the commissioning activities.
The commissioning activities are to coordinate the various tasks of each subsystem whenever necessary to accomplish the successful operation of the fully-equipped detector with the target sensitivity and duty factor.
Independent installation/integration activities of each subsystem are not included in the scope of commissioning.

## Slide 3: Goal for phase 1
Strict requirement: operation of the cryogenic 3km Michelson interferometer by Mar. 30, 2018
  Mar. 31 reserved for a test run
However, we should complete the phase 1 operation as soon as possible.

## Slide 4: Stages in Phase 1
There are four stages in Phase 1:
Stage 1 (Oct. 2 - End of Oct.)
  Alignment up to BS (inclusive)
Stage 2 (Dec.)
  Alignment of ETMy
Stage 3 (Feb.)
  Locking of MI with Cryogenic ETMy with Calibrated sensitivity curve
Stage 4 (Mar.)
  Locking of MI in vacuum with cryogenic ETMx/y with data stored
Test run (One day before cooling Xend; exact period:TBD)
  Characterization of various systems for Phase 2
(No PRMI operation after test run)

## Slide 5: Stage 1
Initial status
  Beam from IMMT2 roughly aligned to PRM and BS
  PRM, PR2, PR3, and BS installed and integrated

## Slide 6: Rough Schedule
 | 9/25-9/29 | 10/2-10/6 | 10/10-10/13 | 10/16-10/20 | 10/23-10/27 | 10/30-11/2 | 11/6-11/10 | 11/13-11/17 | 11/20-11-24
BS integration |  |  |  |  |  |  |  |  | 
Preparation of EXA |  |  |  |  |  |  |  |  | 
Preparation of EYA |  |  |  |  |  |  |  |  | 
Preparation of IXA |  |  | Goggles |  |  |  |  |  | 
Preparation of IYA |  |  | Goggles | Goggles |  |  |  |  | 
Placement of beam tubes, etc. |  |  |  |  |  | Schedule: TBD |  |  | 
Preparation of laser |  |  |  |  |  |  |  |  | 
Alignment of IMMT2, PR2 |  |  | Goggles |  |  |  |  |  | 
Alignment of PR3 |  |  |  | Goggles |  |  |  |  | 
Alignment of BS |  |  |  |  | Goggles |  |  |  | 
Measurement of beam position at IXC, IYC (*1) |  |  |  |  |  | Schedule: TBD |  |  | 
Measurement of BS/PR relative position to tanks (*2) |  |  |  |  |  | Schedule: TBD |  |  | 
Laser hazard area | Upstream of IFI line (*a) |  | 1st floor of center area and Upstream of EXA/EYA line (*b) |  |  | TBD depending on the schedule of *1 and *2; *a for *2, *b for *1 |  |  | 

## Slide 7: Laser hazard area
 | 9/25-9/29 | 10/2-10/6 | 10/10-10/13 | 10/16-10/20 | 10/23-10/27 | 10/30-11/2 | 11/6-11/10 | 11/13-11/17 | 11/20-11-24
Upstream of IFI |  |  |  |  |  |  |  |  | 
Center area, the 1st floor |  |  |  |  |  | TBD |  |  | 
Center area, the 2nd floor |  |  |  |  |  |  |  |  | 
EXA |  |  |  |  |  |  |  |  | 
EYA |  |  |  |  |  |  |  |  | 
EXC |  |  |  |  |  |  |  |  | 
EYC |  |  |  |  |  |  |  |  | 
End area, the 2nd floor |  |  |  |  |  |  |  |  | 
Arm tunnel |  |  |  |  |  |  |  |  | 

## Slide 8: Preparation (EXA/EYA)
Preparation of Chambers (CRY)
  Expose the EYA to air
  Loosen the bellows and Install the flange behind the EXA/EYA
Miscellaneous preparation (Uchiyama)
  Clean the EXA/EYA area with Korokoro
  Place G-mat on the floor
  Various goods
    Check of the goods used for iKAGRA
    Purchase of necessary goods
      消耗品類（ベンコット、アルコール、ウエットティッシュ等）
      工具（メガネレンチ、トルクレンチ）を調達。
      クリーンウエアに着替える際に必要なハンガー等を調達。
  Cover viewports with Aluminum foil
Preparation of laser hazard area and goggles (Kawamura)

## Slide 9: Preparation (IXA/IYA)
Cleaning of the area (CRY)
Chambers (CRY)
  Expose IXA/IYA to air
  Not necessary to remove stuff from IXC
  Partially remove stuff from IYC
Miscellaneous preparation (Uchiyama)
  Place G-mat on the floor
  Various goods
    消耗品類（ベンコット、アルコール、ウエットティッシュ等）
    工具（メガネレンチ、トルクレンチ）等
    クリーンウエアに着替える際に必要なハンガー等
    バスマット
Preparation of laser hazard area and goggles (Kawamura)

## Slide 10: Placement of Beam tubes, etc.
PR2-PR3 beam tube (VAC)
  Install PR2-PR3 beam tube with the connection part covered by aluminum foil instead of installing the bellows, Inject dry air into PR2-PR3 beam tube
  Oct. 2 - 6
BS assembly frame (VIS)
  Remove BS assembly frame
  Oct. 2 - 6
BS-beam tubes (VAC)
  Install BS beam tube with the connection part covered by aluminum foil instead of installing the bellows, Inject dry air into BS-beam tube
  Bellows will be connected to the gate valve, but not to the tank???
  Oct. 2 - 6
IFI-IMM, IMM-PRM, PRM-PR3
  TBD (after alignment and measurement; probably November)

## Slide 11: Preparation of input optics
Send Laser beam to MIF (IOO)
  Increase laser power to appropriate level
  Bellows will not be put until November.

## Slide 12: Alignment
Alignment up to virtual positions of ETMx/ETMy
  10/10 – 10/13: Misalign PRM by a known amount (MIF, VIS), Align IMMT2 (MIF, IOO) and PR2 (MIF, VIS)
  10/16 – 10/20: Align PR3 by monitoring beam in IXA and EXA (MIF, VIS)
  10/23 – 10/27: Align BS by monitoring beam in IYA and EYA (MIF, VIS)
  Notes
    Cables for PD can be put through between the tank and flange.
Moving of passageway (Uchiyama)
  Remove the passageway for each chamber during the alignment work
  (During the no-passageway period workers should pass by the wall outside the clean booth.)

## Slide 13: Position measurement
Measurement of beam spot in IXC/IYC with respect to chambers (Uchiyama)
  Accuracy: 1mm?
  Flange in the upper part may or may not be there.
  Moving of passageway
    Remove the passageway for each chamber during the alignment work
    (During the no-passageway period workers should pass by the wall outside the clean booth.)
Measurement of the relative position of BS/PR with respect to chambers (VIS)
  No beam condition is necessary.

## Slide 14: Vacuum check
TBD
Check the vacuum system
Check the misalignment caused by evacuation

## Slide 15: Stage 2
Initial status
  Beam from BS to virtual positions of ETMx/ETMy finely aligned
  ETMy installed and integrated in the air at room temperature

## Slide 16: Activities
Alignment of ETMy
  Align ETMy to IFI (MIF, DGS, VIS, CRY, IOO)
  Lead MI-REFL beam outside the chamber (MIF, IOO)
Installation and alignment of MI-REFL output optics
  Install and align MI-REFL output optics using the beam reflected by ETMy (MIF)
Bellows connection and evacuation of the EYC/EYA (CRY)

## Slide 17: Stage 3
Initial status
  MI aligned except ETMx
  ETMx installed in the air at room temperature
  EYC evacuated

## Slide 18: Activities
RT model for LSC and calibration (DGS, MIF, CAL)
Global control between LSC and VIS models (DGS, MIF, VIS)
Alignment, locking, optimization, characterization of MI
  Align ETMy to IFI (MIF, DGS, VIS, CRY, IOO)
  Make a fine alignment of MI (MIF)
  Lock MI (MIF)
  Optimize and characterize MI (MIF)
Installation and alignment of MI-AS output optics (MIF, VIS)
Cooling-down of ETMy (CRY)
  鏡角度の追跡 シフト？
Calibration (CAL)

## Slide 19: Stage 4
Initial status
  MI locked
  ETMy cooled down

## Slide 20: Activities
Bellows connection and evacuation of the EXC/EXA and cooling-down of ETMx (VAC, CRY)
Bellows connection and evacuation of the whole vacuum system in the center area (VAC)
Re-alignment, re-locking, optimization, characterization of MI (MIF)
Guardian scripts for PSL/IMC/MI (DGS, IOO, MIF)
Data pipe line (DAS)
Physical environment monitors (DetChar)
Selection of monitoring signals (DGS)

## Slide 21: Expected final status
The whole vacuum chamber evacuated
ETMx/ETMy cooled down
MIF re-aligned, locked, optimized
Automatic operation for MI
Detchar system
Various signals integrated into data acquisition system
Various signals monitored at control room

## Slide 22: Laser hazard area
The laser hazard area should be set for the minimum area not to disturb necessary installation/integration work.

## Slide 23: Organization of commissioning team
Organization
  Leader: Kawamura
  Sub-leader: Miyakawa
With the help of
  Scheduler: Uchiyama
  MIF chief: Michimura
  Each subsystem chief/subchief
The commissioning team is a subset of SEO.

## Slide 24: Role of commissioning team
The team establishes the detailed schedule following the overall schedule established by SEO and scheduler.
The team coordinates work of each subsystem to follow the detailed schedule.
At least one of the team members stays at the site everyday during the commissioning period.
When a possible delay of the schedule is anticipated, the team tries to manipulate the order of daily work, etc. to meet the schedule if possible. If not, the team reports to the SEO and asks for the remedy.
The MIF chief helps the team by suggesting the optimized procedure of the commissioning task from the standpoint of the interferometer operation.

## Slide 25: Meeting
The commissioning leader runs a weekly remotely-accessible meeting with the help of sub-leaders inside the “Kotei-kaigi” to discuss activities on the previous week and on the coming weeks.
  The team encourages people off site to attend the weekly meeting remotely to provide their inputs.
  Should the commissioning meeting separated from the Kotei-kaigi?
The leader runs a daily remotely-accessible meeting inside the “Chorei” to discuss activities on the previous day and on the day .
  The team encourages people off site to attend the daily meeting remotely to provide their inputs.

## Slide 26: Remote operation (under discussion)
In principle the remote operation from anywhere other than Kamioka (KAGRA site and control room) is prohibited.
If absolutely necessary, remote operation is possible under the following conditions:
  The remote operation should be approved by the commissioning team in advance.
  The corresponding researcher should be present at Kamioka.
  The remote operation should be mentioned in the daily meeting in Chorei.
The remote viewing is OK.

## Slide 27: TBD
We will talk with each subsystem group to optimize the detailed schedule.
  When should the GIF data be implemented in the digital system.
  What kind of evaluation and measurement should be done at each stage?
  When should the bellows in the central area be connected. When should the whole vacuum system in the center area be evacuated? Before or after the first half of the test run?
How long should the test run last?