## Sheet1
BS
Complete assy drawings
Replace IP base (Box)
Make blade springs to suspend the bread board+damper
Test NIKHEF ACC to replace the geophone
Replace broken small flex joint
Assemble IP+TF
Prepare for jigs (gluing, hanging, assembly)
PR3 modification
Design damping system for BF
Make damping system for BF
Disassemble suspension
PR2
Design damping system for BF
Make damping system for BF
PRM
Design damping system for BF
Make damping system for BF
Procure Inner frame
Make traverser
Make payload parts
SRM/2/3
Complete assy drawings
Make IP base (Box)
Make blade springs to suspend the bread board+damper
Transport IP, TF, SF
Assemble IP+TF
Check optimum load of SF
Type-A
Transport IP, TF, SF
Assemble IP+TF
Set IP base (Box)
Set top chamber
Design EQ stop
Procure EQ stop
Make long Maraging rod
Check optimum load of SF
Assemble BF in ATC
IMMT (ETM for iKAGRA)
Disassemble TAMA suspension
Clean TANA suspension
Make coil
Check picomotor