## Sheet1
Group name | Place | Task name | January | [25 empty] | February |  | Additional information
|  |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
|  |  | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tue. | Wed. | Thur. | Fri. | Sat. | Sun.
| ITMX | Yaw FR installation | bar: January 17 to January 18
| ETMY | LVDT Calibration | bar: January 8
Release IP | bar: January 21 to January 25
| ETMX | Yaw FR installation | bar: January 10
Fix the tower | bar: January 9
| BS | Blade inspection | bar: January 8
Install Geophones | bar: January 8 to January 10
New FR installation | bar: January 8 to January 11; January 15 to January 16
IP tuning | bar: January 15 to January 16
| SRM | Adjusted the pitch | bar: January 7 to January 11
Installed OpLev viewports | bar: January 7 to January 11
Fix the FR | bar: January 15
Test Yaw stepper | bar: January 15
IP tuning | bar: January 16
Service Geophones | bar: January 16 to January 17
Install Geophones | bar: January 18
Height check | bar: January 16
Hook LBB | bar: January 17
| SR2 | Install OpLev | bar: January 21 to January 25
Height check | bar: January 16
| SR3 | Height check | bar: January 16
| SR | Height measurement | bar: January 15
| PR2 | Cable repair | bar: January 8 to January 9
Install new EQ stop plate | bar: January 16
| OSTM | Installation into chamber | bar: January 15 to January 16
Gluing | bar: January 8 to January 11