## Sheet1
|  |  |  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016
No. | Sub No. | Subsub No. | Work Description | 1stQ | 2ndQ | 3rdQ | 4thQ | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 |  |  | raw data spool and transfer (2014 before stating iLCGT test run, brush up until bLCGT start). This task is to construct raw data spool at Kamioka facility, and send data to Kashiwa continuously.
| 1 |  | fix the specification of the hardware (2013 1stQ) | bar: 2012 1stQ to 2013 1
| 2 |  | workstation install (2013 end) | bar: 2013 2 to 2013 4
| 3 |  | data transfer test (2014 1stQ) | bar: 2014 1
| 4 |  | DAQ software implement and test run (2014 2ndQ) | bar: 2014 2
| 5 |  | Observational Run (start at iLCGT/bLCGT operation)
|  | 1 | Watchdog human resource arrangement (2014 2ndQ, 2016 end) | bar: 2014 2; 2016 4
|  |  |  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016
No. | Sub No. | Subsub No. | Work Description | 1stQ | 2ndQ | 3rdQ | 4thQ | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
2 |  |  | primary data processing (pre-process) to generate and re-pack the calibrated data (2014 before stating iLCGT test run, brush up until bLCGT start). This task is to pre-process data as 'analysis ready' not only in format, but also in first level data qualifying and calibration.
| 1 |  | software development of calibration method, making h(t) (2014 1stQ) | bar: 2012 1stQ to 2014 1
| 2 |  | detector characterization (2014 1stQ, end of 2016, improve after 2016) | bar: 2014 1; 2016 4
| 3 |  | tuning main data transfer to Kashiwa as for reliability (2016 end) | bar: 2016 4
| 4 |  | low latency transfer for followup observation (2014 2ndQ) | bar: 2014 2
|  |  |  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016
No. | Sub No. | Subsub No. | Work Description | 1stQ | 2ndQ | 3rdQ | 4thQ | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
3 |  |  | storage of raw and calibrated data (partially 2014 2ndQ, full 2016 end) This task is about storage and management of raw/calibrated (= pre-processed) data at Kashiwa. | bar: 2014 2
| 1 |  | fix the specification of the hardware (end of 2012) | bar: 2012 1stQ to 2012 4thQ
| 2 |  | procurement (2013). We need a official bid, but I don't know partial storage system for iLCGT is not so large as for international bid. | bar: 2013 1 to 2013 4
| 3 |  | install hardware at Kashiwa for iLCGT (2014 2ndQ) | bar: 2014 2
| 4 |  | data transfer test (2014 1stQ) | bar: 2014 1
| 5 |  | RUN for iLCGT (2014 last half) | bar: 2014 3 to 2014 4
| 6 |  | shakedown data archiver/management software (2014 2ndQ, 2016 end) | bar: 2014 2; 2016 4
| 7 |  | procurement (2015). Full storage system may require the international bit. | bar: 2015 1 to 2015 4
| 8 |  | install full archiver with several PByte at Kashiwa (2016 end) | bar: 2016 4
| 9 |  | Tier 2 of LCGT data branch (2016 ?) | bar: 2016 1 to 2016 4
|  |  |  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016
No. | Sub No. | Subsub No. | Work Description | 1stQ | 2ndQ | 3rdQ | 4thQ | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
4 |  |  | computing platform (hardware) This task is to prepare computing hardwares for data analysis except for LCGT data storage.
| 1 |  | fix the requirement of calculation performance (2012 1stQ) | bar: 2012 1stQ
| 2 |  | fix specification, may be with ICRR platform (? 2012 end ?) | bar: 2012 1stQ to 2013 1
| 3 |  | end-user clients (2014 2ndQ, 2016, and opportunity maintenance) | bar: 2014 2; 2016 1 to 2016 4
|  |  |  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016
No. | Sub No. | Subsub No. | Work Description | 1stQ | 2ndQ | 3rdQ | 4thQ | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
5 |  |  | computing environment (software). This task is to build data analysis software environment.
| 1 |  | research LSC and Virgo (2011). LSC/VIRGOでどのように解析をやっているのか調査するという意味か？ ＜ーそうです
| 2 |  | immigrate software from LSC/Virgo (2013, if it's allowed.). これは2012年早々にやるべきでは？ ＜ー2013は完成時期（ほかの（）の時期もそう）。前倒しには神田も賛成。というわけで右のチャートの開始時期を前にしてみます。MOUの制限は？ということ。 | bar: 2012 1stQ to 2014 1
| 3 |  | LCGT simulation data (2012 end). LCGTのmock h(t)データのこと？ ＜ーそんなイメージです。なるべく本物と同じデータ構造（各種チャンネル、フラッグも）を持つダミーデータ。 | bar: 2012 1stQ to 2012 4thQ
| 4 |  | LCGT's borne program (2012 end) "borne"プログラムとは具体的に何か？LSCソフトウェア移植前に"borne program"を作るのか？ ＜ー"bone"はもっとも基本的／典型的な解析ルーチンで、たとえばスペクトルを出してなにがしかの値を計算する、といったもの。エンドユーザー、院生が最初に取りかかれるよう、導入の役割を果たすものを準備する。 LSCのソフトを利用する部分もあるとおもう。一方で、転送系に使う部分などは、自作しないと上手くゆかないと思われる。 | bar: 2012 1stQ to 2012 4thQ
|  |  |  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016
No. | Sub No. | Subsub No. | Work Description | 1stQ | 2ndQ | 3rdQ | 4thQ | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
6 |  |  | data distribution partially among LCGT collaborators. This task is data distribution within the LCGT collaboration.
| 1 |  | design of tier (2014) | bar: 2012 1stQ to 2013 3
| 2 |  | distribute partially (2014) | bar: 2013 4 to 2014 4
| 3 |  | complete mirroring (?)
|  |  |  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016
No. | Sub No. | Subsub No. | Work Description | 1stQ | 2ndQ | 3rdQ | 4thQ | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
7 |  |  | data sharing with international gravitational wave detectors, This task is about data distribution among international scientist groups (outside LCGT Collaboration).
| 1 |  | immigrate and test transfer software (2012) | bar: 2012 1stQ to 2012 4thQ
| 2 |  | dummy data exchange (2013? according to LIGO/Virgo) | bar: 2013 1 to 2013 4
| 3 |  | data exchange (maybe decided by MOU)
|  |  |  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016
No. | Sub No. | Subsub No. | Work Description | 1stQ | 2ndQ | 3rdQ | 4thQ | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
8 |  |  | search for gravitational waves (2014 3rdQ, after 2016 continuously). This task is about gravitational wave event search pipelines. These sub-tasks are same to various gravitational wave sources: 8A: Compact Binary Coalescence 8B: Burst 8C: Continuous 8D: Stochastic 8E: (more optional)
| A1 |  | bone program (2012 end) "bone program"とは何か？LSCソフトウェア移植前に"bone program"作るのか？ ＜ー上記同様だが、細分化したタスクの上では、エンドユーザーよりはパイプライン全体の骨と成る構造のデザイン、と思ったほうがよい。 | bar: 2012 1stQ to 2012 4thQ
| A2 |  | pipeline design (2013 2ndQ) | bar: 2012 1stQ to 2013 2
| A3 |  | pipeline implementation (2014 2ndQ) | bar: 2013 3 to 2014 2
| A4 |  | process observation data (2014 3rdQ, 2016-) | bar: 2014 3 to 2014 4; 2016 1 to 2016 4
| A5 |  | simulation study (2014 2ndQ, 2016-) | bar: 2014 2; 2016 1 to 2016 4
| 6 |  | simulation data (2013 end, but should be partially released.). Simulated signalのこと？ ＜ーそうです。 LSCソフトウェア移植前に"simulation data"作るのか？ ＜ー可能な部分は進めたい。デッドコピーではいけないだろう。 | bar: 2012 1stQ to 2013 4
|  |  |  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016
No. | Sub No. | Subsub No. | Work Description | 1stQ | 2ndQ | 3rdQ | 4thQ | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
9 |  |  | mutually followup with counterpart observations, e.g. X-ray, gamma-ray observatories (2014 3rdQ, after 2016 continuously) This task is about gravitational wave event search. | bar: 2014 3; 2016 1 to 2016 4
| 1 |  | study/research how to follow-up (2013 end, we will update continuously.) | bar: 2012 1stQ to 2013 4
| 2 |  | low latency event trigger (partially 2014 3rdQ, 2016 end, we will update continuously.) | bar: 2014 3; 2016 1 to 2016 4
| 3 |  | data base (2017?) イベントのデータベースを作成するということ？ ＜ー公開用のデータベースのことを想定しています。
|  |  |  | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016
No. | Sub No. | Subsub No. | Work Description | 1stQ | 2ndQ | 3rdQ | 4thQ | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
10 |  |  | analyze gravitational wave events, learn physics of their sources, develop gravitational wave physics and astronomy. (2014 3rdQ, after 2016 continuously) Extract scientific results from observation data, not only discovery of events, but also physics/astrophysics of GW sources. | bar: 2014 3; 2016 1 to 2016 4