## Slide 1: LCGT Vacuum System
111128 VAC (YS)
ETMY
ITMY
ETMX
ITMX
IP
TMP
DRY P
BS
PRM
PR3
PR2
SRM
SR3
SR2
PD
MCF
MC
3000 m
double chambers (2.4 and 1.5 m in dia.)
//GASF + I-Pendulum + cryogenic//
chambers (1.5 m in dia./2 m for BS)
//GASF + I-Pendulum//
chambers (2 m in dia.)
//stack + D-Pendulum//
iLCGT
iLCGT
MMT

## Slide 2: LCGT Vacuum System
111128 VAC (YS)
ETMX
2014 (H26) - Apr
iLCGT
double chambers (2.4 and 1.5 m in dia.)
//GASF + I-Pendulum + cryogenic//

## Slide 3: LCGT Vacuum System
111128 VAC (YS)
ETMX
TMP
DRY P
3000 m
double chambers (2.4 and 1.5 m in dia.)
//GASF + I-Pendulum + cryogenic//
iLCGT
2014 (H26) - Aug

## Slide 4: LCGT Vacuum System
111128 VAC (YS)
ETMX
ITMX
IP
TMP
DRY P
BS
PRM
PR3
PR2
SRM
SR3
SR2
PD
MCF
MC
3000 m
double chambers (2.4 and 1.5 m in dia.)
//GASF + I-Pendulum + cryogenic//
chambers (1.5 m in dia./2 m for BS)
//GASF + I-Pendulum//
chambers (2 m in dia.)
//stack + D-Pendulum//
iLCGT
iLCGT
MMT
2014 (H26) - Sep
ITMY

## Slide 5: LCGT Vacuum System
111128 VAC (YS)
ETMY
ITMY
ETMX
ITMX
IP
TMP
DRY P
BS
PRM
PR3
PR2
SRM
SR3
SR2
PD
MCF
MC
3000 m
double chambers (2.4 and 1.5 m in dia.)
//GASF + I-Pendulum + cryogenic//
chambers (1.5 m in dia./2 m for BS)
//GASF + I-Pendulum//
chambers (2 m in dia.)
//stack + D-Pendulum//
iLCGT
iLCGT
MMT
2015 (H27) - Mar

## Slide 6: LCGT Vacuum System
● expected schedule for installing
manufacturing
1) manufacturing 500 of tubes; 30 24 months (April 2011 - September March 2013）.
2) manufacturing chambers (w/o type A); 12 18 months (October 2012- March 2014 ).
installing
1) installing chambers in X end; April 2014.
2) installing tube in X arm; 9 5 months (April 2014 - August 2014).
3) installing chambers in Center Room; September 2014.
4) installing tube in Y arm; 9 6 months (October 2014 to March 2015).
5) pumping down; will be finished a few months later after the last installation of tube.
    ** expected pump-down scheme
      to 1 Pa; few days by dry-pump
      to 10-6 Pa; 50 hours by TMP
      to 10-7 Pa; 500 hours by IP
111128 VAC (YS)